## 1. Equality Actions
Please click on the filter icon displayed in the header of each column to sort and / or filter the data by your preferred option(s).
Head of Service | Reporting Officer | Service Plan Reference | Action | Quarter 1 (April - June 2016) | Quarter 1 on track? (R/A/G) | Comments / Further action (Q1) | Quarter 2 progress (July - September 2016) | Quarter 2 on track? (R/A/G) | Comments / Further action (Q2) | Quarter 3 (October - December 2016) | Quarter 3 on track? (R/A/G) | Comments / Further action (Q3) | Quarter 4 (January - March 2017) | End of Year Acheived? (R/A/G) | Comments (Q4)
Mark Rizk | Rachel Liddle | EH05 | Climate Change Policy EHIA (October 2016) |  | Not yet due |  |  | On track to be achieved |  |  | Fully Achieved |  |  | Fully Achieved
Mark Rizk | Rachel Liddle | EH05 | Climate Change Adaptation Plan EHIA (September 2016) |  | Not yet due |  |  | Fully Achieved |  |  | Fully Achieved |  |  | Fully Achieved
Mark Rizk | Rachel Liddle | EH06 | Housing Enforcement Policy EHIA (July 2016) |  | Not yet due |  |  | Fully Achieved |  |  | Fully Achieved |  |  | Fully Achieved
Mark Rizk | Rachel Liddle |  | Corporate Enforcement Policy EHIA (July 2016) |  | Not yet due |  |  | Fully Achieved |  |  | Fully Achieved |  |  | Fully Achieved
Mark Rizk | Rachel Liddle |  | Noise Management Policy EHIA (October 2016) |  | Not yet due |  |  | On track to be achieved |  |  | Fully Achieved |  |  | Fully Achieved
Sal Khan | Brett Atkinson |  | The Tenancy Strategy EHIA (2016) |  | On track to be achieved |  |  | Fully Achieved |  | Review of strategy has not resulted in changes that would require an EHIA. | Fully Achieved |  |  | Fully Achieved
Mark Rizk | Neil Brown |  | Sports Development Strategy EHIA (January 2017) |  | Not yet due |  |  | Not yet due |  |  | Not yet due |  |  | Deferred | Deferred until 2017-18, new strategy to be written in line with the Leisure options review.
Mark Rizk | Andy Mason |  | Neighbourhood Working EHIA (March 2017) |  | Fully Achieved |  | Completed for CMT Aug 2016 | Fully Achieved |  | Completed for CMT Aug 2016 | Fully Achieved |  | EIA was completed in August 2016 when report went to cabinet | Fully Achieved
Sal Khan | James Abbott |  | Data Quality Strategy EHIA (2016) |  | Not yet due |  |  | Not yet due |  | Review of strategy has not resulted in changes that would require an EHIA. | Fully Achieved |  | Achieved in Q3 | Fully Achieved
Sal Khan | Anna Miller/Jeff Upton |  | Open Spaces and Playing Pitch Strategy EHIA (2016/17) | Work has begun on the procurement stage of evidence gathering. | On track to be achieved |  |  | Not yet due |  | Until 2017/18 | Deferred |  |  | Deferred
Sal Khan | Sarah Richardson |  | Council Tax Reduction Scheme Policy EHIA (November 2016) |  | Not yet due |  | No changes to current scheme, as approved by EDR June 2016. | Fully Achieved | EHIA will be reviewed in 2017 for 2018 scheme | Achieved in quarter 2 | Fully Achieved |  | Council Tax Reduction Scheme was not changed for 2017/18, therefore a revised EHIA was not required. | Deferred | If there are any changes to the scheme it will need to be approved by the Council, and therefore a revised EHIA will be completed for that purpose
Andy O'Brien | Linda McDonald | HRP1 | Appeals Against Dismissal Policy EHIA (2016) |  | On track to be achieved |  |  | Fully Achieved | Reviewed as part of policy refresh June 2016 - no changes |  | Fully Achieved |  | EHIA review completed June 2016 | Fully Achieved
Andy O'Brien | Linda McDonald | HRP1 | Employment of Related Persons Policy EHIA (2016) |  | On track to be achieved |  | Reviewed as part of policy refresh - no actions identified | Fully Achieved |  | Reviewed as part of policy refresh in quarter 2 - no actions identified | Fully Achieved |  | Reviewed June 2016 | Fully Achieved
Andy O'Brien | Linda McDonald | HRP2 | Discolure & Barring Service Procedures EHIA (2016) |  | Not yet due |  |  | Not yet due | to be completed by end Nov 2016 | Completed November 2016 | Fully Achieved |  | Completed November 2016 | Fully Achieved
Andy O'Brien | Linda McDonald | HRP3 | Flexible Working Policy EHIA (2016) |  | Not yet due |  |  | Not yet due |  |  | On track to be achieved | to be completed Q4 as part of policy review | Completed March 2017 | Fully Achieved
Andy O'Brien | Linda McDonald | HRP3 | Home Working Policy EHIA (2016) |  | Not yet due |  |  | Not yet due | to be completed by end Nov 2016 | Completed November 2016 | Fully Achieved |  | Completed November 2016 | Fully Achieved
Andy O'Brien | Linda McDonald | HRP3 | Family Friendly Provisions Policy EHIA (2016) |  | Not yet due |  |  | Not yet due |  |  | On track to be achieved | to be completed Q4 as part of policy review | Completed February 2017 | Fully Achieved
Completed behind schedule
Deferred
Deleted
Completed behind schedule
Off Target
On track to be achieved
Fully Achieved
Update not provided
Not yet due
Completed Behind Schedule
Deferred
Deleted
Update not Provided
Fully Achieved
Off Target

## 2. Status tracking
Head of Service | Reporting Officer | Reference | Action | Quarter 1 (April - June 2016) | Quarter 2 (July - Sept 2016) | Quarter 3 (Oct to Dec 2016) | Quarter 4 (Jan to March 2017)
Mark Rizk | Rachel Liddle |  | Climate Change Policy EHIA (October 2016) | Not yet due | On track to be achieved | Fully Achieved | Fully Achieved
Mark Rizk | Rachel Liddle |  | Climate Change Adaptation Plan EHIA (September 2016) | Not yet due | Fully Achieved | Fully Achieved | Fully Achieved
Mark Rizk | Rachel Liddle |  | Housing Enforcement Policy EHIA (July 2016) | Not yet due | Fully Achieved | Fully Achieved | Fully Achieved
Mark Rizk | Rachel Liddle |  | Corporate Enforcement Policy EHIA (July 2016) | Not yet due | Fully Achieved | Fully Achieved | Fully Achieved
Mark Rizk | Rachel Liddle |  | Noise Management Policy EHIA (October 2016) | Not yet due | On track to be achieved | Fully Achieved | Fully Achieved
Sal Khan | Brett Atkinson |  | The Tenancy Strategy EHIA (2016) | On track to be achieved | Fully Achieved | Fully Achieved | Fully Achieved
Mark Rizk | Neil Brown |  | Sports Development Strategy EHIA (January 2017) | Not yet due | Not yet due | Not yet due | Deferred
Mark Rizk | Andy Mason |  | Neighbourhood Working EHIA (March 2017) | Fully Achieved | Fully Achieved | Fully Achieved | Fully Achieved
Sal Khan | James Abbott |  | Data Quality Strategy EHIA (2016) | Not yet due | Not yet due | Fully Achieved | Fully Achieved
Sal Khan | Anna Miller/Jeff Upton |  | Open Spaces and Playing Pitch Strategy EHIA (2016/17) | On track to be achieved | Not yet due | Deferred | Deferred
Sal Khan | Sarah Richardson |  | Council Tax Reduction Scheme Policy EHIA (November 2016) | Not yet due | Fully Achieved | Fully Achieved | Deferred
Andy O'Brien | Linda McDonald |  | Appeals Against Dismissal Policy EHIA (2016) | On track to be achieved | Fully Achieved | Fully Achieved | Fully Achieved
Andy O'Brien | Linda McDonald |  | Employment of Related Persons Policy EHIA (2016) | On track to be achieved | Fully Achieved | Fully Achieved | Fully Achieved
Andy O'Brien | Linda McDonald |  | Discolure & Barring Service Procedures EHIA (2016) | Not yet due | Not yet due | Fully Achieved | Fully Achieved
Andy O'Brien | Linda McDonald |  | Flexible Working Policy EHIA (2016) | Not yet due | Not yet due | On track to be achieved | Fully Achieved
Andy O'Brien | Linda McDonald |  | Home Working Policy EHIA (2016) | Not yet due | Not yet due | Fully Achieved | Fully Achieved
Andy O'Brien | Linda McDonald |  | Family Friendly Provisions Policy EHIA (2016) | Not yet due | Not yet due | On track to be achieved | Fully Achieved

## 3. Percentages
Equality Objectives - Quarter One | [6 empty] | Equality Objectives - Quarter Two
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | R / A / G status | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | R / A / G status | Total % of due indicators
Target Fully Achieved | 1 | 5.882% | 29.41% | 20% | G | 100% | Target Fully Achieved | 8 | 47.06% | 58.82% | 80% | G | 100%
On Track to be Achieved | 4 | 23.53% |  | 80% |  |  | On Track to be Achieved | 2 | 11.76% |  | 20%
In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | A | 0% | In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | A | 0%
Completed Behind Schedule | 0 | 0% | 0% | 0% | R | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | R | 0%
Off Target | 0 | 100% |  | 340% |  |  | Off Target | 0 | 100% |  | 170%
Not yet due to be reported | 12 | 70.59% | 70.59% |  |  |  | Not yet due to be reported | 7 | 41.18% | 41.18%
Update not provided | 0 | 0% | 0% |  |  |  | Update not provided | 0 | 0% | 0%
Deferred | 0 | 0% | 0% |  |  |  | Deferred | 0 | 0% | 0%
Deleted | 0 | 0% | 0% |  |  |  | Deleted | 0 | 0% | 0%
Totals | 17 | [5 empty] | Totals | 17
Due to be Reported | 5 | [5 empty] | Due to be Reported | 10
Equality Objectives - Quarter Three | [6 empty] | Equality Objectives - Quarter Four
Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | R / A / G status | Total % of due indicators | Status | Number of measures | % of all indicators | Total % of all indicators | % of due indicators | R / A / G status | Total % of due indicators
Target Fully Achieved | 13 | 76.47% | 88.24% | 86.67% | G | 100% | Target Fully Achieved | 14 | 82.35% | 82.35% | 100% | G | 100%
On Track to be Achieved | 2 | 11.76% |  | 13.33% |  |  | On Track to be Achieved | 0 | 0% |  | 0%
In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | A | 0% | In Danger of Falling Behind Target | 0 | 0% | 0% | 0% | A | 0%
Completed Behind Schedule | 0 | 0% | 0% | 0% | R | 0% | Completed Behind Schedule | 0 | 0% | 0% | 0% | R | 0%
Off Target | 0 | 0% |  | 0% |  |  | Off Target | 0 | 0% |  | 0%
Not yet due to be reported | 1 | 5.882% | 5.882% |  |  |  | Not yet due to be reported | 0 | 0% | 0%
Update not provided | 0 | 0% | 0% |  |  |  | Update not provided | 0 | 0% | 0%
Deferred | 1 | 5.882% | 5.882% |  |  |  | Deferred | 3 | 17.65% | 17.65%
Deleted | 0 | 0% | 0% |  |  |  | Deleted | 0 | 0% | 0%
Totals | 17 | [5 empty] | Totals | 17
Due to be Reported | 15 | [5 empty] | Due to be Reported | 14

## 4. Charts
Charts | Please note that all charts shown below can be amended to be displayed in alternative styles. Please right click on the relevant chart, select "change chart type" and choose your preferred chart option.
Overall Performance 2016-17
|  |  | Q1 | Q2 | Q3 | Q4 | Q2 | Q3 | Q4
|  | Green | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Amber | bar: Q1 to Q4
Red | bar: Q1 to Q4