## Cover Sheet
Project: Burton upon Trent Towns Fund - Project D
Risk Register owner: -
Contact details: -
Version: 1.2 (September 2022)

## Risk Scoring Matrix
Likelihood | Almost Certain | 7 | 11 | 14 | 16 | Likelihood of Occurrence – Threats
| Probable | 4 | 8 | 12 | 15 | Estimation | Description | Indicators
| Possible | 2 | 5 | 9 | 13 | Almost Certain | Likely to occur each year or > 25% chance of occurrence | Potential of it occurring > 3 times in 10 years;
| Unlikely | 1 | 3 | 6 | 10 |  |  | Has occurred in past two years
|  | Minor | Moderate | Major | Catastrophic | Probable | Probable to occur in a 10 year time period or less than 25% chance of occurrence but more than 10% chance (between 1 in 4 and 1 in 10 chance) | Could occur up to 3 times in 10 years.
|  | Impact | [5 empty] | Could be difficult to control due to some external influences.
Is there a history of occurrence?
LOW RISKS | [5 empty] | Possible | Possible to occur in a 10 year time period or a 10% chance of occurrence (1 in 10 chance) | Could occur once
Unlikely Likelihood and Minor Impact |  |  |  | = Score 1 |  |  |  | Possible but not probable that it will occur
Possible Likelihood and Minor Impact |  |  |  | = Score 2 |  | Unlikely | Not likely to occur in 10 year time period or less than 2% chance of occurrence | Has not occurred.
Unlikely Likelihood and Moderate Impact |  |  |  | = Score 3 |  |  |  | Unlikely to occur.
Probable Likelihood and Minor Impact |  |  |  | = Score 4
Possible Likelihood and Moderate Impact |  |  |  | = Score 5 |  | Likelihood of Occurrence – Opportunities
[6 empty] | Estimation | Description | Indicators
MEDIUM RISKS | [5 empty] | Almost Certain | Favourable outcome likely to be achieved in 1 year; or better than 75% chance of occurrence. | Clear opportunity which can be relied upon with reasonable certainty, to be achieved in the short term based on current management processes.
Unlikely Likelihood and Major Impact |  |  |  | = Score 6 |  | Probable | Reasonable prospects of favourable results in one year of 25% to 75% chance of occurrence. | Opportunities achievable with careful management.
Almost Certain Likelihood and Minor Impact |  |  |  | = Score 7 |  |  |  | Opportunities which may arise over and above the plan.
Probable Likelihood and Moderate Impact |  |  |  | = Score 8 |  | Possible | Some chance of favourable outcome in the medium term of between 25% and 10% chance of occurrence. | Possible opportunity which has yet to be fully investigated by management.
Possible Likelihood and Major Impact |  |  |  | = Score 9 |  |  |  | Opportunity for which the likelihood of success is low on the basis of management resources currently applied.
Unlikely Likelihood and Catastrophic Impact |  |  |  | = Score 10 |  | Unlikely | Not likely to have a favourable outcome or less than 2% chance of occurrence | Unlikely opportunity which has yet to be supported by management.
Opportunity for which the likelihood of success is very low on the basis of management resources currently applied.
HIGH RISKS
Almost Certain Likelihood and Moderate Impact |  |  |  | = Score 11 |  | Risk Consequences – Threats and Opportunities (Impact)
Probable Likelihood and Major Impact |  |  |  | = Score 12 |  | Catastrophic | · Financial impact > £100,000
Possible Likelihood and Catastrophic Impact |  |  |  | = Score 13 |  |  | · Significant impact on Council’s strategy or operational activities for example the corporate strategy, corporate targets and/or corporate plan activities
Almost Certain Likelihood and Major Impact |  |  |  | = Score 14 |  |  | · Significant stakeholder concern e.g. real risk of fatality / severe injury / bad publicity i.e. reputational risk
Probable Likelihood and Catastrophic Impact |  |  |  | = Score 15 |  | Major | · Financial impact between £25,000 and £100,000
Almost Certain Likelihood and Catastrophic Impact |  |  |  | = Score 16 |  |  | · Major impact on the Council’s strategy, reputation or operational activities
· Major stakeholder concern e.g. low risk of injury
[6 empty] | Moderate | · Financial impact between £5,000 and £25,000
· Moderate impact on the Council’s strategy, reputation or operational activities
· Moderate stakeholder concern
[6 empty] | Minor | · Financial impact less than £5,000
· Low impact on the Council’s strategy, reputation or operational activities
· Low stakeholder concern

## Risk Register 1.0 (03-22)
Risk Register
Project: | Burton Project D
Date: | February 2022
Version: | 1
Situation: | Submission of Towns Fund Business Case
Risk ID | Risk Category | Risk Description | Status | Liklihood (1-4) | Impact (1-4) | Risk Rating | Mitigating Action | Risk Owner
1 | Client specific | Partner engagement - The risk of not demonstrating effective engagement with all stakeholder groups (including Statutory bodies) resulting in delayed approvals and potential planning objections. | Open | 2 | 2 | 5 | To continue to engage with partners and others through ongoing dialogue, including through the established governance arrangements. | ESBC
2 | Construction | Ground conditions prove challenging following surveys. | Open | 2 | 3 | 9 | Ground condition surveys to be conducted at earliest opportunity. Procurement strategy to transfer risk to contractors. | ESBC
3 | Environment | Political - The risk that the scheme lacks support from key political stakeholders. | Open | 2 | 4 | 13 | Updates to local politicians through Council usual channels | ESBC
4 | Environment | Brexit - Potential risks arising from Brexit in terms of financial markets, supply-chains, economic circumstances and demand. | Open | 2 | 4 | 13 | To continue monitor proposals in relation to Brexit and adjust the scheme as necessary. | ESBC
5 | Environment | Subsidy Control (State Aid) - the risk that the interventions do not comply with latest Subsidy Control regulations. | Open | 1 | 4 | 10 | Legal advice to be sought by ESBC. | ESBC
6 | Environment | Flood risk – regenerating areas close to the Washlands. | Open | 2 | 4 | 13 | Robust flood defences around the Washlands area. Flood risk assessment to be conducted. | ESBC
7 | External | Demand risk (Market risk) - The risk of not having a sufficient understanding of the needs of leisure and tourism sectors post covid and their future requirements. | Open | 2 | 3 | 9 | Continual review of service requirements and future operating models. | ESBC
8 | External | Concerns about the unknown future of retail in Burton, including the current health of the high street and high streets across the country as a whole. | Open | 3 | 3 | 12 | Continual review of service requirements and future operating models. | ESBC, future Occupiers
9 | External | Climate – risk of unknown climate impacting on the area. | Open | 1 | 3 | 6 | The Council will incorporate Climate Change/Emergency thinking into project design. | ESBC
10 | Finance | Capital costs - The risks that the costs of delivering the interventions are greater than currently identified. | Open | 2 | 4 | 13 | Continue to refine costs as project is brought forward to implementation. Agree contractual arrangements that limit public sector exposure to cost risk. | ESBC
11 | Procurement | Financial stability of delivery/Supply Chain partners - The risk that delivery/supply chain partners cease trading or go into receivership - impact on programme and costs. | Open | 2 | 4 | 13 | Developer to be procured using ESBC's standard capital procurement processes - test financial stability as part of this process. | ESBC
12 | Procurement | Construction risk - The risk that suitable development partners / contractors cannot be secured or are involved only at a late stage in the design process, resulting in project works not being completed on time, to budget or to specification. | Open | 2 | 4 | 13 | Timely selection of development partners /contractors for each individual element/phase of the programme. | ESBC
13 | Project specific | Public sector funding - Risk that additonal funding sought is not secured / delayed. | Open | 2 | 4 | 13 | To submit bid to the LUF. Continue to liaise closely with Cabinet. | ESBC
14 | Project specific | Partnership - The risk of the failure to develop and maintain relationships with delivery partners and other key stakeholders | Open | 2 | 3 | 9 | To continue in the future to engage with delivery partners and stakeholders. | ESBC
15 | Project specific | Community impacts - The risk that local residents / businesses object to proposals. | Open | 3 | 3 | 12 | To continue in the future to engage with local residents and businesses e.g. through further public consultation. | ESBC
16 | Project specific | Unwilling landowners - cannot secure control of land to implement change. | Open | 1 | 4 | 10 | Ongoing discussion with landowner(s). | ESBC
17 | Project specific | Risk of planning approval not being achieved. | Open | 2 | 4 | 13 | Early dialogue between ESBC and the Local Planning Authority | ESBC
18 | Project specific | Project costs increase when detailed design completed. | Open | 3 | 4 | 15 | Consultants to be appointed to undertake detailed design and prepare cost assessment. Work will be undertaken in the context of budgets available | ESBC
19 | Project specific | Concerns that the projects are not realistic and will not materialise. | Open | 2 | 3 | 9 | The Council has undertaken scoping and design work to ensure all interventions are technically and economically viable. | ESBC
20 | Project specific | Concerns of the project having a knock-on effect of new developments could be the increase in traffic and pressure on roads which could in turn increase pollution and environmental issues in the area and detract from people coming to Burton. | Open | 3 | 3 | 12 | Traffic and transport assessments could be undertaken as the project moves forward. | ESBC

## Risk Register 1.1 (08-22)
Risk Register
Project: | Burton Project D
Date: | August 2022
Version: | 1.1
Situation: | Confirmation of Towns Fund monies and submission of LUF2 Bid
Risk ID | Risk Category | Risk Description | Status | Liklihood (1-4) | Impact (1-4) | Risk Rating | Mitigating Action | Risk Owner
1 | Client specific | Partner engagement - The risk of not demonstrating effective engagement with all stakeholder groups (including Statutory bodies) resulting in delayed approvals and potential planning objections. | Open | 2 | 2 | 5 | To continue to engage with partners and others through ongoing dialogue, including through the established governance arrangements. | ESBC
2 | Construction | Ground conditions prove challenging following surveys. | Open | 2 | 3 | 9 | Ground condition surveys to be conducted at earliest opportunity. Procurement strategy to transfer risk to contractors. | ESBC
3 | Environment | Political - The risk that the scheme lacks support from key political stakeholders. | Open | 2 | 3 | 9 | Positive TF update reduces impact of this risk by one level, need for engagement remains. | ESBC
4 | Environment | Brexit - Potential risks arising from Brexit in terms of financial markets, supply-chains, economic circumstances and demand. | Open | 2 | 3 | 9 | To continue monitor proposals in relation to Brexit and adjust the scheme as necessary. No particular impacts identified at this time. | ESBC
5 | Environment | Subsidy Control (State Aid) - the risk that the interventions do not comply with latest Subsidy Control regulations. | Open | 1 | 2 | 3 | External legal advice on subsidy control implications is positive, likelihood of an issue remains low. Impact would also be better managed, with opportunities for resolution. | ESBC
6 | Environment | Flood risk – regenerating areas close to the Washlands. | Open | 1 | 4 | 10 | FRA to be conducted, advice from EA supports a reduction of liklihood on basis of FD levels | ESBC
7 | External | Demand risk (Market risk) - The risk of not having a sufficient understanding of the needs of leisure and tourism sectors post covid and their future requirements. | Open | 2 | 3 | 9 | Engagement with partners and operators is positive, though risk remains level 9. | ESBC
8 | External | Concerns about the unknown future of retail in Burton, including the current health of the high street and high streets across the country as a whole. | Open | 3 | 2 | 8 | Lower impact following non-inclusion of retail in submission. To monitor with partners otherwise and remain open. | ESBC, future Occupiers
9 | External | Climate – risk of unknown climate impacting on the area. | Open | 1 | 3 | 6 | The Council will incorporate Climate Change/Emergency thinking into project design. Allowances have also been built into the LUF2 bid. | ESBC
10 | Finance | Capital costs - The risks that the costs of delivering the interventions are greater than currently identified. | Open | 3 | 4 | 15 | Largest area of risk, opportunity to refine costs as project is brought forward to implementation. Agree contractual arrangements that limit public sector exposure to cost risk/leverage private investment. | ESBC
11 | Procurement | Financial stability of delivery/Supply Chain partners - The risk that delivery/supply chain partners cease trading or go into receivership - impact on programme and costs. | Open | 1 | 3 | 6 | Consideration been given to utilising an existing framework agreement, which builds resilience into the commission. Risk is consequently lowered on both factors. | ESBC
12 | Procurement | Construction risk - The risk that suitable development partners / contractors cannot be secured or are involved only at a late stage in the design process, resulting in project works not being completed on time, to budget or to specification. | Open | 2 | 4 | 13 | Intention to 'early engage' through framework process, so contractors are part of the design process. Risk level remains unchanged at this time, pending further detail. | ESBC
13 | Project specific | Public sector funding - Risk that additonal funding sought is not secured / delayed. | Open | 2 | 2 | 5 | Towns Funding has been approved, full £23.8m resulting in circa £20m for this project to deliver the full scope of Phase 1. Risk is reduced, but not closed, following the submission of the LUF2 bid, which would deliver some elements of Phase 2 (leisure and Bass House repair/F&D). | ESBC
14 | Project specific | Partnership - The risk of the failure to develop and maintain relationships with delivery partners and other key stakeholders | Open | 2 | 3 | 9 | To continue in the future to engage with delivery partners and stakeholders. Engagement on the visitor centre element is so far positive. | ESBC
15 | Project specific | Community impacts - The risk that local residents / businesses object to proposals. | Open | 3 | 3 | 12 | Reviewing engagement plan to commence during project delivery phase. Risk remains unchanged at this time. | ESBC
16 | Project specific | Unwilling landowners - cannot secure control of land to implement change. | Open | 1 | 4 | 10 | Ongoing discussion with landowner, discussion on terms are progressing. | ESBC
17 | Project specific | Risk of planning approval not being achieved. | Open | 2 | 4 | 13 | Existing engagement with LPA and intention for pre-app style advice with conservation and tree officers in coming months. | ESBC
18 | Project specific | Project costs increase when detailed design completed. | Open | 4 | 3 | 14 | Linked to risk 10, inflationary impacts are concerning and may impact scope of proposals. Elements of inflation are built into the programme in line with RICS standard and project design will need to reflect this impact. This is also built into the LUF2 bid. Slight change on risk to confirm more likely but slightly lower impact, as this will be built into design and scope works. | ESBC
19 | Project specific | Concerns that the projects are not realistic and will not materialise. | Open | 1 | 3 | 6 | The Council has undertaken scoping and design work to ensure all interventions are technically and economically viable. Risk liklihood reduced to reflect confirmation of funding. | ESBC
20 | Project specific | Concerns of the project having a knock-on effect of new developments could be the increase in traffic and pressure on roads which could in turn increase pollution and environmental issues in the area and detract from people coming to Burton. | Open | 3 | 3 | 12 | Traffic and transport assessments will be undertaken as the project moves forward. To be undertaken as part of the planning process. | ESBC
21 | Project specific | Risk of LUF2 funding bid not being approved and Phase 2 delivery impacts | Open | 2 | 3 | 9 | Project approved by Council on the basis of Phase 1 delivery, options for bringing forward Phase 2 outside of LUF2 bid will be explored. | ESBC

## Risk Register 1.2 (09-22)
Risk Register
Project: | Burton Project D
Date: | September 2022
Version: | 1.2
Situation: | MCBC confirmed relocation, closure of National Brewery Centre and proposal for Bass House museum
Risk ID | Risk Category | Risk Description | Status | Liklihood (1-4) | Impact (1-4) | Risk Rating | Mitigating Action | Risk Owner
1 | Client specific | Partner engagement - The risk of not demonstrating effective engagement with all stakeholder groups (including Statutory bodies) resulting in delayed approvals and potential planning objections. | Open | 2 | 3 | 9 | To continue to engage with partners and others through ongoing dialogue, including through the established governance arrangements. Higher impact as new pool of stakeholders to be engaged. | ESBC
2 | Construction | Ground conditions prove challenging following surveys. | Open | 2 | 3 | 9 | Ground condition surveys to be conducted at earliest opportunity. Procurement strategy to transfer risk to contractors. | ESBC
3 | Environment | Political - The risk that the scheme lacks support from key political stakeholders. | Open | 3 | 3 | 12 | Increased likelihood to reflect current situation (NBC) and how this may affect political support for the High Street project. Updates through comms channels needed to mitigate impact. | ESBC
4 | Environment | Brexit - Potential risks arising from Brexit in terms of financial markets, supply-chains, economic circumstances and demand. | Open | 2 | 3 | 9 | To continue monitor proposals in relation to Brexit and adjust the scheme as necessary. No particular impacts identified at this time. | ESBC
5 | Environment | Subsidy Control (State Aid) - the risk that the interventions do not comply with latest Subsidy Control regulations. | Open | 1 | 2 | 3 | External legal advice on subsidy control implications is positive, likelihood of an issue remains low. Impact would also be better managed, with opportunities for resolution. | ESBC
6 | Environment | Flood risk – regenerating areas close to the Washlands. | Open | 1 | 4 | 10 | FRA to be conducted, advice from EA supports a reduction of liklihood on basis of FD levels | ESBC
7 | External | Demand risk (Market risk) - The risk of not having a sufficient understanding of the needs of leisure and tourism sectors post covid and their future requirements. | Open | 2 | 3 | 9 | Risk level remains unchanged at this time, though there is now a new market to consider (to be reviewed as a separate risk). | ESBC
8 | External | Concerns about the unknown future of retail in Burton, including the current health of the high street and high streets across the country as a whole. | Open | 3 | 2 | 8 | Lower impact following non-inclusion of retail in submission. To monitor with partners otherwise and remain open. | ESBC, future Occupiers
9 | External | Climate – risk of unknown climate impacting on the area. | Open | 1 | 3 | 6 | The Council will incorporate Climate Change/Emergency thinking into project design. Allowances have also been built into the LUF2 bid. | ESBC
10 | Finance | Capital costs - The risks that the costs of delivering the interventions are greater than currently identified. | Open | 3 | 4 | 15 | Largest area of risk, opportunity to refine costs as project is brought forward to implementation. Agree contractual arrangements that limit public sector exposure to cost risk/leverage private investment. Need to review post-LUF2 outcome. | ESBC
11 | Procurement | Financial stability of delivery/Supply Chain partners - The risk that delivery/supply chain partners cease trading or go into receivership - impact on programme and costs. | Open | 1 | 3 | 6 | Consideration been given to utilising an existing framework agreement, which builds resilience into the commission. Risk is consequently lowered on both factors. | ESBC
12 | Procurement | Construction risk - The risk that suitable development partners / contractors cannot be secured or are involved only at a late stage in the design process, resulting in project works not being completed on time, to budget or to specification. | Open | 2 | 4 | 13 | Intention to 'early engage' through framework process, so contractors are part of the design process. Risk level remains unchanged at this time, pending further detail. | ESBC
13 | Project specific | Public sector funding - Risk that additonal funding sought is not secured / delayed. | Open | 2 | 3 | 9 | LUF2 funding required to deliver Phase 2 of project, including Bass House works - impact is now one level higher. Expecting LUF2 decision by November, with alternative options to be explored (HLF, gift aid, Arts Council, private investment). To be reviewed post-decision. Phase 1 remains on track. | ESBC
14 | Project specific | Partnership - The risk of the failure to develop and maintain relationships with delivery partners and other key stakeholders | Open | 2 | 4 | 13 | Need to engage new partners/stakeholders regarding the NBC and expand the remit of the historian working group. Impact is one level higher. | ESBC
15 | Project specific | Community impacts - The risk that local residents / businesses object to proposals. | Open | 3 | 3 | 12 | Risk rating remains a 12 at this time. Plans being developed for the creation of a regeneration engagement hub that will support the messaging of project updates throughout the delivery of the project. Impacted by NBC closure and perception of causality to High Street project. | ESBC
16 | Project specific | Unwilling landowners - cannot secure control of land to implement change. | Open | 1 | 4 | 10 | Contract discussions progressing. Impacted by NBC announcement and how this affects the project. | ESBC
17 | Project specific | Risk of planning approval not being achieved. | Open | 2 | 4 | 13 | Existing engagement with LPA and intention for pre-app style advice with conservation and tree officers in coming months. | ESBC
18 | Project specific | Project costs increase when detailed design completed. | Open | 4 | 3 | 14 | Linked to risk 10, inflationary impacts are concerning and may impact scope of proposals. Elements of inflation are built into the programme in line with RICS standard and project design will need to reflect this impact. This is also built into the LUF2 bid. Will be built into design and scope works. | ESBC
19 | Project specific | Concerns that the projects are not realistic and will not materialise. | Open | 2 | 3 | 9 | Increased likelihood to reflect new scope of project for Bass House, need early engagement with relevant stakeholders and partners to devleop the proposals for this property. | ESBC
20 | Project specific | Concerns of the project having a knock-on effect of new developments could be the increase in traffic and pressure on roads which could in turn increase pollution and environmental issues in the area and detract from people coming to Burton. | Open | 3 | 3 | 12 | Traffic and transport assessments will be undertaken as the project moves forward. To be undertaken as part of the planning process. | ESBC
21 | Project specific | Risk of LUF2 funding bid not being approved and Phase 2 delivery impacts | Open | 2 | 3 | 9 | Project approved by Council on the basis of Phase 1 delivery, options for bringing forward Phase 2 outside of LUF2 bid will be explored. | ESBC
22 | Project specific | Risk of new museum proposal being undeliverable | Open | 2 | 4 | 13 | Engagement with relevant stakeholders and funding bodies to explore feasibilty work for project viability. | ESBC
23 | Project specific | Feasibility work on museum demonstrate requirement for further funding | Open | 2 | 3 | 9 | To review post-LUF2 outturn in the context of approved TF monies and possible external funding routes - engagement on HLF bid needed. | ESBC
24 | Project specific | Lack of support for museum proposal / impact of low interest (tourism/visit perspective) | Open | 2 | 3 | 9 | Engagement proposal (risk 15) would mitigate this risk through regular communication on project delivery (open days, consultations, tours etc). | ESBC
25 | Project specific | Requirement for the Council to revenue fund new museum proposal | Open | 2 | 2 | 5 | Any delivery option requiring revenue support would need Member approval and so this is not a current impact. To be reviewed post-project development/feasibility when this risk can be qualified and quantified. Revenue impact of maintaining buildings currently is as per Council decision on Phase 1 delivery. | ESBC